TRUSTEES OF THE CALIFORNIA STATE UNIVERSITY

REQUEST FOR PROPOSAL

NO. [XXXX]

SYSTEMWIDE ENERGY STORAGE

MEA PROJECTS

Energy Storage Site License and Service Agreement and All Addenda

PROJECT NO. [XX-XXX]

Campus Specific Storage MEA Coversheet and attachments

[Campus to Insert Completed Battery MEA Coversheet and Attachments]

Table of Contents

1.	SECTION– OVERVIEW	6

1.1.	PURPOSE	6

1.2.	SUMMARY	6

1.3.	SCHEDULE OF EVENTS	6

1.4.	TERM	6

1.5.	ENERGY STORAGE SITE LICENCE SERVICE AGREEMENT (ESSLSA)	7

1.6.	QUESTIONS	7

1.7.	SUBMISSION OF PROPOSALS	7

2.	SECTION – RFP GENERAL PROVISIONS	7

2.1.	COMPLETION OF PROPOSAL	7

2.2.	REJECTION OF PROPOSALS	7

2.3.	CANCELLATION OF PROPOSAL	8

2.4.	COST OF PROPOSALS	8

2.5.	USE OF PROPOSALS	8

2.6.	ALTERNATIVE PROPOSALS	8

2.7.	ADDENDA	8

2.8.	NON-COLLUSION AFFIDAVIT	8

2.9.	ERRORS AND OMISSIONS	8

2.10.	CONFIDENTIALITY	8

2.11.	ON-ENDORSEMENT	8

2.12.	DISPUTES	8

2.13.	PROTESTS	8

3.	SECTION– PROCUREMENT REQUIREMENTS	9

3.1.	PREVAILING WAGE	9

3.2.	INSURANCE	9

3.3.	CONTRACTOR’S LICENSE INFORMATION	9

3.4.	SMALL BUSINESS PREFERENCE	9

3.5.	DISABLED VETERAN BUSINESS ENTERPRISE (DVBE) AND INCENTIVES	9

4.	SECTION SCOPE OF SERVICES	9

4.1.	SPECIFICATIONS AND REQUIREMENTS	9

4.2.	DESIGN	10

4.3.	CONSTRUCTION	11

4.4.	Electric Power Requirements:	12

4.5.	ENERGY STORAGE SYSTEM INSTALLATION	12

4.6.	RULE 21 APPLICATION	13

4.7.	UTILITY GRID INTERCONNECTION	13

4.8.	METERS AND MONITORING	13

4.9.	WIRE, CABLE, CONDUIT AND CONNECTORS	13

4.10.	STRUCTURAL REQUIREMENTS	14

4.11.	OPERATIONS AND MAINTENANCE	14

4.12.	EMERGENCY SHUT DOWN	14

4.13.	COMMISSIONING AND ACCEPTANCE TEST	14

4.14.	WARRANTIES AND GUARANTEES	14

4.15.	TRAINING AND MAINTENANCE MANUALS	14

4.16.	LIGHTING	15

4.17.	RECORD DOCUMENTS	15

4.18.	PAINT	15

4.19.	PERMITS AND ENVIRONMENTAL CLEARANCES	15

4.20.	STRUCTURAL REQUIREMENTS AND CEQA	15

4.21.	CONSTRUCTION COMPLETION AND LIQUIDATED DAMAGES	15

4.22.	PERFORMANCE GUARANTEE REQUIREMENTS	16

4.23.	RESTORATION OF SITE	16

4.24.	TREES, LIGHT POLES AND BOLLARDS	16

4.25.	GUIDELINES	16

5.	SECTION TECHNICAL PROPOSAL REQUIREMENTS AND EVALUATION	16

5.1.	SYSTEM SIZE AND OUTPUT	17

5.2.	SYSTEM LOCATIONS AND LAYOUTS	17

5.3.	TECHNICAL DESCRIPTION	17

5.4.	METERING & MONITORING DESCRIPTION WITH DATA ACCESS	18

5.5.	PROJECT SCHEDULE	18

5.6.	PROJECT TEAM ORGANIZATION	19

5.7.	QUALIFICATIONS OF KEY PERSONNEL	19

5.8.	PAST-PROJECT EXPERIENCE	19

5.9.	REFERENCES	20

5.10.	MANAGEMENT AND STAFFING PLAN	20

5.11.	OPERATION AND MAINTENANCE PLAN	20

5.12.	BILLING PLAN	20

5.13.	Exceptions to ESSLSA	21

5.14.	CAPITAL FINANCE STRUCTURE	21

5.15.	SUSTAINABILITY CAPABILITIES	21

5.16.	SIMULATED PEAK DEMAND REDUCTION	21

6.	SECTION COST PROPOSAL	22

6.1.	COST PROPOSAL SUBMITTAL	22

6.2.	ACTUAL PEAK DEMAND REDUCTION PRICE	22

6.3.	BASIS FOR AWARD	22

6.4.	ESTABLISHMENT OF SUCCESSFUL PROPOSAL	22

6.5.	AWARD	22

6.6.	NOTICE OF INTENT TO AWARD	22

7.	SECTION 7 – PREPARATION AND FORMAT	24

7.1.	NUMBER OF COPIES	24

7.2.	DELIVERY OF PROPOSALS	24

7.3.	PROPOSAL FORMAT	24

FORMS

FORM 1 - SMALL BUSINESS PREFERENCE AND CERTIFICATION

FORM 2 - DISABLED VETERANS BUSINESS ENTERPRISE (DVBE)

FORM 3 - SUSTAINABILITY CAPABILITIES

FORM 4 - EXPECTED AND GUARANTEED PEAK DEMAND REDUCTION

# SECTION– OVERVIEW

# PURPOSE

The purpose of this Request for Proposal (RFP) is to solicit proposals from the System Providers selected from the Systemwide Energy Storage Master Enabling Agreement (MEA).

Multiple awards are possible from this RFP for Energy Storage Site License and Service Agreements (ESSLSAs) depending on how many campus coversheets are included with this RFP.

# SUMMARY

System Provider shall finance, design, engineer, construct, own, operate, and maintain, energy storage systems and sell storage services to Trustees on a 10th of a cent/kW (AC) basis at a competitive rate, pursuant to fully-executed 3rd party owned and operated energy storage license and service agreements at locations described in the Campus Specific Energy Storage MEA coversheet.

System provider shall also submit a cost proposal with a cash purchase price that at the campus’ sole option may be selected.

Proposer shall be solely responsible for all costs related to, and necessary for, the implementation and on- going operations of the energy storage systems as proposed. In addition, Proposer should reference Section 3.9, Transaction Fee, within the Energy Storage License and Services Agreement (ESSLSA) which shall reimburse the Trustees for incurred project costs.

Proposer should assume there was no pre-feasibility evaluation done to appropriately energy storage systems for any of the locations and conditions offered. Proposer is responsible for ascertaining relevant site conditions and making its own findings and determinations regarding appropriate system sizes and associated energy production.

The integration of each on-site energy storage system with the electrical systems serving the site will be the responsibility of the Proposer.  Proposers shall assume $250,000 in Rule 21 interconnection costs and complete the schedule below in the event actual costs are less than or greater than $250,000.  In no event, shall the Peak Demand Reduction rate be permitted to exceed the Campus Hurdle Rate on the Campus Specific Energy Storage MEA Coversheet.

| Change in interconnection costs | Change in Peak Demand Reduction Price ($/KW) |
| --- | --- |
| -$50,000 |  |
| -$40,000 |  |
| -$30,000 |  |
| -$20,000 |  |
| -$10,000 |  |
| +$10,000 |  |
| +$20,000 |  |
| +$30,000 |  |
| +$40,000 |  |
| +$50,000 |  |

Proposals will be evaluated using a points system. The quality points (600 points) will be added to the cost proposal points (400 points) for a total point score. The cost proposal points will be determined using the following formula:  Total cost proposal points will be awarded based on the price per peak demand reduction measured in KW. Price per peak demand reduction measured in KW will be calculated by the Trustees using the tariff rate(s) for demand charges, as reflected in the bid sheets. Total cost proposal points will be scored in direct relation to the price per peak demand variance from the lowest price. The lowest price will receive the maximum score of 400 points.  The proposal offering the highest total points specified in the RFP will be recommended for award by the Trustees at its sole discretion.

# SCHEDULE OF EVENTS

The schedules contained in the campus specific storage MEA coversheet outline critical timelines associated with the RFP and subsequent award. System Provider may be disqualified for failing to adhere to the dates and times specified below (all times Pacific [Daylight or Standard]Time):

The Trustees reserve the right to adjust this schedule at any time.

# TERM

The Term of this Agreement is described in the Campus Specific Energy Storage MEA coversheet and shall commence on the Effective Date and shall continue for the period indicated from the Commercial Operation Date of the System unless terminated earlier pursuant to the provisions of the ESSLSA.

# ENERGY STORAGE SITE LICENCE SERVICE AGREEMENT (ESSLSA)

The Energy Storage Site License Service Agreement (ESSLSA) has been memorialized in the Energy Storage Master Enabling Agreement. The terms of the ESSLSA include a definition of the scope of work, requirements for the use of Trustees facilities, construction and installation requirements, operations and maintenance provisions, insurance requirements, pricing mechanism, billing requirements, termination rights, events of default, default remedies, assignment, termination fee, end of term provisions, including option to buy out the system, and other terms and conditions. Upon award, Successful Proposer shall sign and be responsible for complying with the terms and conditions of the ESSLSA as agreed to in the Energy Storage Master Enabling Agreement.

# QUESTIONS

All questions, interpretations or clarifications, either administrative or technical regarding this RFP must be submitted in writing and directed to the staff identified in the Campus Contact Information for Solicitation field of the campus Specific Energy Storage MEA Coversheet. All questions submitted will be answered in writing and conveyed via written addenda to all Proposers. Oral statements concerning the meaning or intent of the contents of this RFP by any person is unauthorized and invalid. The deadline for all questions is located on the Campus specific Energy Storage MEA coversheet.

# SUBMISSION OF PROPOSALS

Technical Proposals and Cost Proposals must be delivered to Campus Contact provided on the Campus Specific Energy Storage MEA Coversheet on or before the time and date set forth in the Request for Proposal. PROPOSALS WILL NOT BE RECEIVED AT ANY OTHER LOCATION. It is the Proposer’s responsibility to ensure that both proposals are received at the correct time and place. Mistakes or delays in the mail or other means of delivery employed by the Proposer are entirely the responsibility of the Proposer. LATE SUBMITTALS WILL NOT BE ACCEPTED.

Technical Proposals:

Technical Proposals must be received on or before the date and time indicated on the Campus Specific storage MEA Coversheet. Sealed packages shall be marked as follows:

Technical Proposal

Systemwide Energy Storage MEA

California State University,

[Campus Name From Energy Storage Coversheet]

Proposer’s Name and Address

Cost Proposals:

Cost proposals must be submitted on the Cost Proposal Form provided by the Trustees, on or before the date and time indicated on the Campus Specific Energy Storage MEA Coversheet. Sealed envelope shall be marked as follows:

Cost Proposal

Systemwide Storage MEA

California State University,

[Campus Name from Energy Storage Coversheet]

Proposer’s Name and Address

# SECTION – RFP GENERAL PROVISIONS

# COMPLETION OF PROPOSAL

Proposals shall be completed in all respects as required by the RFP provisions. A proposal may be rejected if conditional, incomplete, inaccurate in its representation, or if it contains any alterations of form or other irregularities of any kind. Proposals which contain false or misleading statements, or which provide references that do not support an attribute(s) or conditions(s) claimed by the Proposer, may be rejected. All statements made by the Proposer shall also be without ambiguity and with adequate elaboration where necessary for clear understanding.

# REJECTION OF PROPOSALS

The Trustees reserve the right to reject any or all proposals and to waive informalities and minor irregularities in proposals received. The Trustees’ waiver of an immaterial defect shall in no way modify the RFP documents or excuse the Proposer from full compliance with the specifications if proposer is awarded an Agreement. Proposals which include terms and conditions other than the Trustees terms and conditions, may be rejected as being non-responsive.

# CANCELLATION OF PROPOSAL

This solicitation does not obligate the Trustees to enter into an Agreement. The Trustees reserve the right to cancel this RFP at any time, for any reason deemed in the best interests of the Trustees. No obligation either expressed or implied, exists on the part of the Trustees to make an award or to pay any costs incurred in the preparation or submission of a proposal.

# COST OF PROPOSALS

All costs associated with responding to this Request for Proposal are entirely the responsibility of the Proposer and shall not be chargeable in any way to the Trustees.

# USE OF PROPOSALS

The Trustees may use any or all ideas or concepts presented in any proposal without compensation to the Proposer. Selection or rejection of the proposal does not affect this right. All materials submitted in response to this RFP will become the property of the Trustees.

# ALTERNATIVE PROPOSALS

Proposer shall submit only one proposal. Multiple proposals will result in the rejection of all proposals submitted by the Proposer.

# ADDENDA

The Trustees may modify this Request for Proposal or any of its contents or attachments, prior to the date fixed for submission of proposals by issuance of a written addendum. All Addenda will be dated and numbered consecutively.  All addenda must specifically be acknowledged and accepted in the proposal.

# NON-COLLUSION AFFIDAVIT

By signing the proposal response, Proposer hereby certifies that the proposal is not made in the interest of, or on behalf of, any undisclosed party; that the proposal is genuine and not collusive, false, or sham; that the proposer has not directly or indirectly induced or solicited any other proposer to put in a false or sham bid, and has not directly or indirectly agreed with any proposer or anyone else to put in a false or sham bid, or to refrain from bidding; that the Proposer has not in any manner, directly or indirectly, sought to fix any overhead, profit or cost element of the bid, of that of any other Proposer, or to secure any advantage against the public body awarding the contract or anyone interested in the proposed contract.

# ERRORS AND OMISSIONS

Before submitting a response to this solicitation, Proposers should thoroughly review and identify any and all errors or omissions for clarification and confirm compliance requirements with the RFP. Proposers should submit all relevant inquiries regarding contents of the RFP, including the ESSLSA in a timely manner in accordance with the RFP timelines.

# CONFIDENTIALITY

The Trustees shall make every effort to protect the confidentiality of submitted proposals however, Proposer clearly understands California State University, is a public entity subject to disclosure laws.

# ON-ENDORSEMENT

Once a proposal is accepted and an award is made, the successful Proposer shall not issue any news releases or other statements pertaining to the award or servicing of the Agreement which state or imply Trustees endorsement of Proposer’s services.

# DISPUTES

The Trustees encourage all Proposers to resolve issues regarding the requirements or the procurement process through written correspondence and discussions. The Trustees wish to foster cooperative relationships and to reach fair and objective resolutions in a timely manner. In the event a Proposer feels that the specifications and/or requirements may be unfair or unreasonable, written notification must be submitted to the Contracts and Procurement Office prior to the scheduled proposal submittal deadline.

# PROTESTS

Proposer’s filing a protest must do so within three (3) working days after Notice of Intent to Award is issued. The Proposer shall submit a full and complete written statement detailing the facts in support of the protest. Protests must be sent by certified or registered mail, or delivered in person to the Director, or designee, at the Campus Contact Information for Solicitation listed on the Campus Specific Energy Storage MEA Coversheet.

An impartial evaluator(s) selected by the Trustees shall perform a review of the protest. Selection of the evaluator shall be at the discretion of the campus. The evaluator shall review the merits and timeliness of the protest and submit a decision in writing within ten (10) working days. The decision will be sent via email or certified or registered mail, to the protesting firm. THE DECISION OF THE TRUSTEES IS FINAL.

# SECTION– PROCUREMENT REQUIREMENTS

# PREVAILING WAGE

Successful Proposer, and any subcontractor thereof shall pay the rate of wages for regular, overtime and holiday work plus employer payments for all benefits generally prevailing in the locality in which the work is to be performed, to the extent required by law, as outlined in the ESSLSA.

# INSURANCE

Prior to commencement of work, Successful Proposer shall provide evidence of insurance as required in the MEA and ESSLSA.

# CONTRACTOR’S LICENSE INFORMATION

The Successful Proposer shall be an individual or firm licensed to do business in California and shall obtain at his/her expense all license(s) and certification(s) required by law for accomplishing any work required in connection with the MEA and ESSLSA.

The following license(s) are required for this solicitation:

- At a minimum, the installation Proposer must have a General Contractor’s license and a C- 10 Electrical Contractor.

- Any licensing or certification requirements as developed and required for the receipt of any subsidies and incentives. These may include, but not necessarily limited to, an active A (General Engineering Contractor, where applicable to unique projects), B (General Contractor), C-10 (Electrical Contractor). For energy storage systems, a Class B license is required.

- Any company that subcontracts installation work to a C-10 must have a Class B license.

# SMALL BUSINESS PREFERENCE

The State of California requires agencies to provide a 5% preference when awarding contracts to small businesses or a non-small business that commits 25% of the contract value to a certified small business. Only small businesses certified by the Office of Small Business and DVBE Services (OSBDS) or a non-small business that commits 25% of the contract value to a certified small business are eligible to receive the preference. Proposers wishing to claim the Small Business Preference must comply with and complete the Small Business Preference and Certification Request Form, Form 1.

# DISABLED VETERAN BUSINESS ENTERPRISE (DVBE) AND INCENTIVES

Disabled Veteran-Owned Business Enterprise participation requirements have been waived for this solicitation in the best interests of the University, however the following DVBE incentives are still offered.

| Proposed DVBE Participation Level | DVBE Incentive % |
| --- | --- |
| 4% to 4.99% | 1% |
| 5% to 5.99% | 2% |
| 6% or more | 3% |

The minimum incentive a qualifying Proposer can receive is 1%. The combination of preferences with a DVBE incentive cannot exceed 10% or $100,000, whichever is less. A non-small business cannot displace a California certified small business from the top-ranked position due to application of preferences or incentive.

# SECTION SCOPE OF SERVICES

# SPECIFICATIONS AND REQUIREMENTS

This Section delineates the minimum technical and installation specifications required of the Successful Proposer by the Trustees for this Project.

The Successful Proposer must guarantee a portion of the peak demand reduction savings as described in Rider C.

The design of the energy storage systems will be the responsibility of the Successful Proposer; however, the systems must be compliant with applicable Trustees design guidelines.

# DESIGN

Proposer shall provide complete architectural, engineering, and consulting services as required to construct the project in all details in accordance with good practice, applicable building codes, CSU guidelines, and this RFP. System design documents shall be prepared, stamped, and signed by an engineer or engineers licensed in the State of California. Proposer also understands that System design documents that are submitted for review without the appropriate professional engineering stamp will not be reviewed and will be returned to Proposer as incomplete and insufficient System documentation.

Successful Proposer shall submit system design documents in three phases, as described in Section IV, paragraph five. System design documents will include, but not be limited to, the following:

- Site plan

- System layout

- System schematics

- System capacity calculations - Power capacity should be included separately for each site location and should be measured at the inverter AC output.

- System production simulations

- System single line electrical diagrams

- Points of interconnection single line electrical diagrams

- Construction documents—plans, elevations, sections, details, specifications, etc.

- Structural calculations and structural and mounting details

- Wind loading and seismic calculations

- List of equipment and materials schedule

- Manufacturers’ data and cut sheets on batteries, inverters and balance of systems equipment

- Geotechnical report as applicable

- Construction Specifications

- Lighting Plan and Photometrics

- Monitoring system design and documentation

- Operations and Maintenance Plan

- Training Plans and training materials

The Successful Proposer agrees to design and construct the System in accordance with all applicable building codes and standards. System design documents will expressly identify the applicable building codes and standards. The system design documents shall be submitted to the Trustees for review and approval. The Successful Proposer shall allow sufficient time in the project schedule for this review to take place and not be less than 10 working days.

Proposer shall:

- Provide comprehensive project management services for the duration of the project, commencing at contract execution. Proposer shall be responsible for assigning a single project manager who will act as the lead for the design and construction phases of the project. Proposer shall be responsible for conducting weekly project management meetings, producing agendas and minutes for the weekly meetings, and keeping an up-to-date issues/actions log.  Proposer shall implement and maintain an internal records management and document control system as required, to support the project. Additionally, Proposer shall be responsible for developing a CPM schedule, which shall be updated and submitted weekly, showing the project’s critical path as well as all activities required to complete the work (including the design, construction, testing, and close-out phases of the project) in sufficient detail to manage the complete scope of the project.  The project schedule shall include all activities necessary to coordinate the work with other parties (e.g., campus, consultants, inspectors, etc.) and will explicitly show the dependencies between all tasks.  At the Trustees’ option, Proposer shall submit the schedule in either MS Project or Primavera format. In addition, schedules must also be submitted in Adobe Acrobat format.

- Conduct detailed site audits and geotechnical studies to confirm the existing site conditions. The geotechnical analysis shall be provided by Proposer and performed by a qualified geotechnical engineering firm. The results of the analysis shall be used when designing the foundations for the structures on the site(s).  As part of the site audit, and upon request of Proposer, Trustees will provide information related to each site, including information regarding: (1) the utility service account number associated with the Site where the System installed; (2) twelve (12) months of billing data for the meter behind which the System will be installed; (3) a general description of Trustees operations at the site; (4) the energy or capacity reductions related to the system and consumption by Trustees at the site;  and (5) a legal description of the physical location of the system and the property where the utility service account associated with the site is located (6) existing geotechnical studies of the site.

- Complete the design for all elements of the project, including but not limited to: civil, structural, electrical, and specialty consulting areas. Drawings shall be prepared and stamped by an engineer (or engineers) licensed in the State of California.

- Incorporate the requirements of permitting agencies as may become apparent in the course of design. The Licensee will apply for and secure all required permits and provide all necessary reports, studies and support required to obtain any permits for any agency that has jurisdiction.

- Include the cost of all permit fees. This comprises the Office of State Fire Marshal, California Environmental Quality Act (CEQA), and Campus Building Inspector.

- Submit design for review at 50% completion of construction documents; at initial 100% completion of construction documents; and after incorporating any corrections and changes required by the Trustees, for back-check of 100% complete construction documents, before commencing construction. After each submittal the Proposer will attend “comments resolution meeting.” The Proposer will review the Trustees comments at this meeting and will be prepared, with the appropriate people in attendance, to resolve the Trustees’ comments. All comments will be resolved to the Proposer’s and the Trustees’ mutual satisfaction. The Trustees may employ peer reviewers at its expense as part of the review process.

- Proposer shall develop and review the construction documents, considering quality of materials and equipment to ensure an efficient design. Proposer shall initiate design decisions by providing information, estimates, schemes, and recommendations regarding construction materials, methods, systems, phasing, and costs that shall provide the highest quality building within the budget and schedule. The plans and specifications shall identify the design codes, standards, and requirements used for the development of the plans, including the edition and applicable sections.

The construction documents shall include a quality control program and an implementation plan to ensure that the completed project complies with the approved project criteria. The design professional-of-record shall specify within the construction documents all tests and inspections that are required by the building code and those that are appropriate to achieve compliance with the ESSLSA. Proposer shall retain the design professional-of record to provide in a professional capacity, timely construction administration services. These services shall include shop drawing review, response to requests for information regarding the construction documents, and periodic visits to the site to observe the quality of the work.

The final, approved-for-construction set of construction documents shall be signed and stamped by the respective California-licensed professionals who prepared the documents, certifying their compliance with codes, standards, practices and regulations. The design professionals-of-record shall retain full responsibility for the design

- Prepare draft Operations and Maintenance Plan to serve two functions: (1) the Plan shall specify the services to be provided, their frequency, and the reporting and documentation that will be made available to the Campus throughout the duration of the project, consistent with the O&M requirements specified herein; and (2) the Plan shall be the basis for preparing the final Operations Manual(s) during the Construction phase.

Provide all submittals on CD in AutoCAD 2015 (or latest version) for drawings and Microsoft Word for specifications; in addition, provide three sets of half-size drawings on white bond paper for all reviews, and three sets of full-size drawings on white bond paper at the time of construction. Provide the As-built Documents on CD as noted above, as well as three sets of full-size As-built Documents on white bond paper at the completion of construction.

# CONSTRUCTION

The Successful Proposer shall construct the Project in accordance with Trustee-approved plans, specifications and submittals prepared by the Licensee to meet or exceed all requirements of the Trustees.

Proposer shall:

- Conduct weekly meetings, as necessary, with the Trustees to provide schedules, status updates and technical input. The Licensee is responsible to provide meeting notes, in electronic format within three (3) working days from conclusion of the meeting.

- Provide required shop drawings and material data submittals. All shop drawings shall be submitted as full-size drawings at a scale usual for the given system, and sufficient to fully show and explain all relevant features, dimensions, etc.

- Provide complete management, supervision, and reporting of all aspects of the construction of this Project, including but not limited to scheduling and conducting weekly meetings with the Trustees.

- Provide resident engineering and contract administration, and pay for all inspections and other related services via the Trustees Transaction Fees, as described in the ESSLSA, including special inspections, necessary for the functional, safe, and on-schedule completion of the Project, starting with the issuance of a Notice-to-Proceed from the Trustees and extending through issuance of Notice of Completion and Acceptance. The Trustees staff will perform inspection to verify compliance with the contract documents.

- Ensure compliance with applicable local, state, and federal codes, building and environmental permit requirements.

- Provide any laboratory, surveying, and other contracted services as required to complete project construction.

- Continue to prepare and maintain a schedule for the duration of a project, consistent with the requirements in Section 4.2, above. The schedule will be updated and presented at the weekly meeting with the Trustees.

- Continue to maintain an internal records management and document control system as required, to support project operations.

- Implement a Safety Program. This includes but is not limited to the following activities:

- Assign a Safety Engineer to monitor and control this program for the Project.

- Develop an on-site Project Safety Plan for review and approval by the Trustees.

- Administer and apply the Trustee approved on-site Project Safety Plan.

- Enforce all Project Safety Plan requirements at all times pertaining to safety and health issues relating to all personnel on the Project Site including workers, consultants, subcontractors, material suppliers, equipment suppliers, and visitors.

- Report accidents, claims, and other on-going safety related issues to the Trustees.

- Adhere strictly to construction access requirements as established by the Trustees and provided in writing during the entire length and scope of the project construction. This shall include the Successful Proposer, its employees, contractors, and/or agents.

- Realistic schedules including a brief narrative of resources and planning should be included. Electrical shutdown needs to be coordinated with the Trustees well in advance, should be conducted during periods when least disruptive to normal operations, and receive prior approval from the Trustees.

# Electric Power Requirements:

Electricity from the System must be provided at 60 Hertz and at the appropriate voltage for electrical interconnection to the Site at the voltage service level, which will be specified by Trustees.

The System components must comply with all standards relevant to the operation and installation of energy storage equipment by UL or other nationally recognized testing facility.  Batteries, enclosures, inverters and components must be certified to comply with the following requirements:

- UL Subject 1741, “Standard for Static Inverters and Charge, Converters, Controllers and Interconnection System Equipment for use with Distributed Energy Resources”

- UL Subject 1973 “Batteries for Use in Light Electric Rail Applications and Stationary Applications”

- UL Subject 1642 “Standard for Lithium Batteries”

- UL Subject 508 “Standard for Industrial Control Panels”

- Any and all requirements as listed by the SGIP incentive program and/or the CEC for the installation of energy storage systems.

- Other codes that will apply include, but are not limited to: ANSI C12.1-2008; (electricity metering)

- NFPA 70 (including NFPA 70E Arc flash)

- IEEE 1547 (interconnections)

# ENERGY STORAGE SYSTEM INSTALLATION

The Proposer shall provide the labor necessary to install all equipment, materials, and components to interconnect to the local utility grid with the exception of required equipment supplied and/or installed by the Trustees.

Installation must comply with the following codes and regulations:

- Systems must be installed in compliance with all applicable State building codes including OSHA and the State Building Standards Code

- NFPA 855, Standard for the Installation of Stationary Energy Storage Systems

- National Electrical Safety Code – ANSI C2-2012

- ANSI/IEEE 519 2014

- 2013 California Code of Regulations Title 24 – California Building Code part 2 - vol. 1 and 2, California Fire Code -part 9, and California Electrical Code – part 3

All Balance of Systems (wiring, component, wiring, conduits, and connections) must be suited for conditions for which they are to be installed. Inverters shall be installed in all-weather enclosures (NEMA4) suitable for exterior location.

# RULE 21 APPLICATION

The Successful Proposer must submit Rule 21 generating facility interconnection applications for each location on campus to local electric utility as described in the campus specific Energy Storage MEA coversheet.  These applications will require new or amended Interconnection Agreements between the campus and local electric utility. The Successful Proposer will comply with any and all operational standards and requirements imposed by the Utility, and comply with the electrical interconnection requirements as stated in the applicable and controlling Utility tariff.

# UTILITY GRID INTERCONNECTION

Proposer shall supply, install, and deliver all equipment required to interconnect to the Trustees’ distribution system and the local utility’s grid. The Proposer shall fulfill all requirements to complete the interconnection process. Proposers shall include a $250,000 allowance for the interconnection.  In the event that actual costs are less than or greater than $250,000 the PPA price shall be adjusted per the table in Section 1.2 and the Cost Proposal Form.  Interconnection standards will comply with all codes and regulations listed in Section 4.4, 4.5, 4.6 4.7 and 4.8.

# METERS AND MONITORING

Successful Proposer will provide two meters per system. Meters shall be a revenue grade Interval Data Recording (IDR) meters for each system complete with any telemetry required by the local electric utility under Rule 21 Interconnection Agreement and the Trustees. The interval data meters must be installed to measure the AC output of the inverters. The meters for the Trustees systems are specified in the campus specific Energy Storage MEA coversheet.

A turnkey data acquisition, data export using representational state transfer (REST) application program interface (API) is strongly preferred. The display system shall be included in the proposal to monitor and track the energy input/output of each  system and to diagnose underperformance. The monitoring system shall be accessible by the Trustees and the public and will track electrical production at maximum 15- minute intervals and with energy totaled by local electric utility time or use periods as specified in ESSLSA.

# WIRE, CABLE, CONDUIT AND CONNECTORS

Contractor shall provide information about proposed wire, cable, and connectors, including all underground facilities. All electrical wiring shall be either copper or aluminum, as indicated on the Campus Specific Energy Storage MEA Coversheet. Cable shall be designed and installed for a service life of 30 years. Cable for DC feeders and interconnect shall be 2-kilovolt 90°C (wet or dry) power cable type USE-2 or RHH/RHW-2 with XLPE jacket and UL 1581, VW-1 rating or approved equal for intended use capable of meeting DC collection system design current requirements. Externally installed cables shall be sunlight and ultraviolet resistant, suitable for direct burial, and conform to NEC 300.5 Underground Installation, Table 300.5 Minimum Cover Requirements, rated to the maximum DC voltage of the System(s). connectors shall be: (i) latching, polarized, and non-interchangeable with receptacles in other systems, and (ii) tap branch connectors with multi-contact termination connectors. Grounding member shall be first to make and last to break contact with mating connector and shall be rated for interrupting current without hazard to operator. Cables shall be listed and identified as wire as stated in NEC Article 690. If a cable tray is utilized, there shall be no self-tapping screws, only a clamping mechanism to secure the top. All underground cable shall be identified in the as-built drawings. Galvanized, rigid metal conduit where underground cable is exposed above ground or stubbed up to junctions or poles shall be used except where protected by concrete caissons. Rigid metal conduit shall be included in the corrosion mitigation plan and shall be designed for a 30-year life in the Site(s) soils and conditions. All 90-degree bends shall follow NEC minimal bend requirements. There shall be no direct burial of cables. No underground cable splicing shall be acceptable under any circumstance. All cable splices shall be brought above ground and housed in a suitable enclosure or, if below grade, placed in a suitable vault that is clearly marked.

# STRUCTURAL REQUIREMENTS

      - All structures shall be designed to resist dead load, live load, plus wind and seismic loads representative of the geographic area.

      - Systems must be able to withstand winds of maximum regional speeds.

      - Thermal loads caused by fluctuations of component and ambient temperatures must be combined with all the above load combinations

      - All  structural  components shall  be  designed  in  a manner commensurate with attaining a minimum 30-year design life. Particular attention shall be given to the prevention of corrosion at the connections between dissimilar metals.

      - As indicated on the Campus Specific Battery MEA Coversheet, paint shall be either powder-coated or baked enamel. In all cases, fascia shall be either powder-coated or baked enamel with a Trustee-selected color.

      - The Trustees will oversee construction for conformance to CSU requirements and standards of care in the field through the Trustees’ Project Manager and the State Fire Marshal.

      - It is also expected the Proposers installer will adhere to any stationary energy storage Guidelines promulgated by the Fire Protection Office of the State Fire Marshal.

# OPERATIONS AND MAINTENANCE

The system is privately-owned by the Successful Proposer; therefore, the Proposer is responsible for all costs associated with operations and maintenance. All system warranties and workmanship guarantees will be in effect during the entire term of the ESSLSA. Services shall include the following:

- The Successful Proposer will be responsible for all necessary maintenance to ensure optimal performance of the systems at the Proposers sole cost and will assure that there will be no disruption to the Trustees’ operations.

- The Proposer shall provide notification to the Trustees as early as practical, but in no event less than five days, prior to any planned repairs or maintenance.

- The Proposer will provide a minimum of ten (10) days notification to the Trustees of any planned repairs or maintenance that will result in interruption to electrical service at any Trustees-owned owned facility.

The Trustees will not provide any maintenance. All system warranties and workmanship guarantees will be in effect during the ESSLSA period.

# EMERGENCY SHUT DOWN

As part of the acceptance of the system by the Trustees, Proposer shall instruct and provide operations manuals on how to shut down the system in the event of an emergency at the Trustees facilities. The Proposer shall insure that emergency first responders can easily identify what to do in the event of an emergency and perform these tasks quickly and safely.

# COMMISSIONING AND ACCEPTANCE TEST

Prior to the commissioning of the system, the Proposer shall:

- Conduct a walk-through with the Trustees and address comments as necessary with to generate a completion punch list and subsequently to confirm all items are complete.

- Administer and coordinate the project contract closeout process and resolve any warranty provision issues.

- Report progress of project contract closeout to the Trustees.

The completeness of the construction will be formally verified by the Trustees against design documents. The Trustees shall observe and verify the system’s performance. The acceptable productive power output will be measured in kW (AC) at the building electrical interconnection point, and must be consistent with the specifications for the system. Approvals as required by the State Fire Marshal and local electric utility will be a pre-requisite for acceptance and for authorization to energize the system(s). A Certification of Acceptance will be issued by the Trustees to the Proposer upon the approval of the Commissioning and Acceptance Test.

# WARRANTIES AND GUARANTEES

The Successful Proposer shall provide evidence of the following warranties:

- Complete  system warranty: minimum 10-year to provide for no-cost repair and replacement of the system for expenses not otherwise covered by manufacturer’s warranties

# TRAINING AND MAINTENANCE MANUALS

The Successful Proposer shall provide training manuals and training sessions for University building operators on emergency operations sequences. Proposer shall provide to the Trustees two (2) sets of site-specific operation, maintenance, and parts manuals for each installed system. These O&M Manuals shall cover all components, options and accessories supplied. The Manuals shall include maintenance, trouble- shooting, and safety precautions specific to the supplied equipment at the site.

# LIGHTING

All systems shall include LED lighting in compliance with Title 24 standards as part of the design and must include occupancy controls. The amount of lighting required is specified by the Trustees in the campus specific Energy Storage MEA coversheet.

# RECORD DOCUMENTS

The Proposer shall also provide one (1) set of As-built Documents in AutoCAD 2015 or higher (for drawings) and Microsoft Word (for specifications). These requirements shall be delivered prior to acceptance of the site- specific system.

# PAINT

All exposed elements (steel, etc.) shall be factory primed and painted per Trustees standards and protocol including quality and color.

# PERMITS AND ENVIRONMENTAL CLEARANCES

The Trustees are self-certifying therefore all building permits are issued by the Trustees, and not local jurisdictions with building and permitting authority.  The Office of the State Fire Marshall is the authority having jurisdiction for Fire Code and the Division of State Architect is the authority having jurisdiction for accessibility review.

The “permit” to install and construct a system at the Trustees host facility will come in the form of a “Notice to Proceed,” after the system plans and drawings have been reviewed and approved for both compliance with the applicable California Building Codes and Standards and achieving constructability requirements as dictated by the Trustees.

Constructability requirements typically mean the system plans and drawings indicate that the system can be installed as engineered and designed, and that the construction schedule, tasks and activities have been reviewed to ensure coordination with host facility operations and requirements. All outside permitting and inspection costs shall be covered by the Proposer.

# STRUCTURAL REQUIREMENTS AND CEQA

Any and all structures and structural elements necessary for the installation and operation of the system shall be designed in accordance with all applicable California Building Codes and Standards that pertain to the erection of such structures.

An analysis of the potential impacts associated with Proposers proposed Systems is required under CEQA. The Successful Proposer shall not commence construction of the Systems until the Trustees have complied with CEQA, per the ESSLSA.

Projects will either be exempt under CEQA, will be addressed by the Trustees, or will be the responsibility of the Proposer, as indicated in the Campus Specific Storage MEA Coversheet.

The Successful Proposer shall provide structural calculations, stamped and signed by a licensed professional structural engineer in good standing with the State of California, as part of the plan check and review requirement.

All structural components shall be designed in a manner commensurate with attaining a minimum 30-year design life (even if the system is warranted for 10 years) and consistent with any host facility specific design guidelines and standards. Particular attention shall be given to the prevention of corrosion at the connections between dissimilar metals such as aluminum and steel, or corrosive soils. Successful Proposer must warrant and maintain the full structural integrity of the system for the full term of the ESSLSA.

The Successful Proposer will be responsible for ascertaining relevant site conditions and making their own finding of appropriate system installation conditions prior to signing the ESSLSA. The Trustees facilities are in an “as is” state of condition, and Proposers should not anticipate that the Trustees host facilities will make any accommodations or efforts to assist in installation of the system.

# CONSTRUCTION COMPLETION AND LIQUIDATED DAMAGES

All construction work shall be completed no later than the Construction Completion Date indicated on the Campus Specific Energy Storage MEA coversheet.

The Successful Proposer shall ensure all affected license areas are fully restored and available for public parking as scheduled.

Liquidated damages will be assessed at a per day cost listed on the Campus Specific Battery MEA coversheet. All such liquidated damages shall be assessed for each day beyond the Construction Completion Date.

# PERFORMANCE GUARANTEE REQUIREMENTS

Proposer must guarantee performance as described in Rider C unless proposing a shared savings model.

# RESTORATION OF SITE

Proposer is responsible for repairing any damage to the existing facilities or grounds that occur as a result of the construction including but not limited to asphalt marking, stains, track marks, cracks, holes, or damage to any vegetation. Proposer shall document all existing conditions prior to the start of construction and executing repair and methods, which are to be reviewed and approved by the Trustees prior to implementation. Asphalt repair shall include two slurry coats and striping.

Contractor is responsible for maintaining the existing functionality of equipment and services impacted by the resulting work; including, but not limited to, existing irrigation functionality and control and lighting. Contractor will be responsible for maintaining current functionality of adjacent lighting that will not be replaced as part of the project.

# TREES, LIGHT POLES AND BOLLARDS

Proposer’s responsibilities for tree trimming and removal shall be as indicated in the Campus Specific Storage MEA Coversheet. All trees requiring trimming or removal shall be identified in the 50% construction document set and shall be approved by the Trustees.  Should the in-lieu fee option be selected in the Campus Specific Storage MEA Coversheet, fees shall be calculated based on the number of trees identified in the 50% construction document set and the current in-lieu fee in effect at the time. Exposed finish should be patched smooth and flush with adjacent grade.

# GUIDELINES

The following guidelines can be found at the following links:

- CSU Access Compliance Design Guidelines

- CSU Mechanical and Electrical Basis of Design Guidelines

- Seismic Requirements

# SECTION TECHNICAL PROPOSAL REQUIREMENTS AND EVALUATION

Proposals will be evaluated by the CSU’s Evaluation Team using a points system. The evaluators will examine each proposal to determine, through the application of uniform criteria, that the Proposer has met the proposal submission requirements. Proposals that have not followed the format, do not meet minimum content and quality standards, or take unacceptable exceptions to the terms and conditions shall be eliminated from further consideration. Proposers should focus on conveying project specific information, excluding generic process information; and editing for brevity.  The Proposal shall be organized with tabs corresponding to Section 7.3 Proposal Format and will be scored based on the Evaluation Criteria and Possible Points Table below.

The CSU will provide the technical score in whole numbers. The CSU will calculate the fee score to two decimal places and will add it to the technical score. The winner will be the Proposer with the highest combined technical and fee scores. In the event of a tie for first place in the total score, the winner will be the tied Proposer with the lowest rate. If the proposed fees are equal the winner will be selected by a coin toss in the presence of both parties and managed by the CSU. The CSU require that the tied Proposers agree to the coin toss procedure in writing before the toss.  The proposal offering the highest point score will be recommended for award. The CSU are under no obligation to award this project to the Proposer whose proposal represents the lowest cost.

Technical proposal Evaluation Criteria and Possible Points Table:

The average of all quality points per category awarded by individual evaluators will be added together to compile a quality points total.

A maximum total of 600 points is available for each proposal as detailed below:

| Criteria | Quality Points |
| --- | --- |
| Energy Storage System Size and Output | 86 |
| System Locations and Layouts | 60 |
| Technical Description | 68 |
| Metering and Monitoring Description with Data Access | 43 |
| Project Schedule | 74 |
| Project Team Organization | 13 |
| Qualifications of Key Personnel | 34 |
| Past Project Experience | 30 |
| References | 13 |
| Management and Staffing Plan | 26 |
| Operations and Maintenance Plan | 64 |
| Billing Plan | 21 |
| Exceptions to ESSLSA | 25 |
| Capital Finance Structure | 17 |
| Sustainability Capabilities | 26 |
| Simulated Peak Demand Reduction Data | Pass/Fail |
| Total | 600 |
| Cost Proposal Points | 400 |
| Total Possible Points | 1,000 |

# SYSTEM SIZE AND OUTPUT

86 POINTS

Include an overview of proposed project including locations and site area to be utilized, including total size (kW/kWh (AC)). Also provide the minimum guaranteed system output (kW/kWh (AC)/year) i.e. the expected and projected Actual Peak Demand Reduction as specified in Rider C.

Expected and guaranteed minimum peak demand reduction kW (AC) for each proposed site and in aggregate, including methodology and assumptions used to develop the estimates; Expected annual system degradation rate over the ten-year term.

# SYSTEM LOCATIONS AND LAYOUTS

60 POINTS

Provide drawings depicting the general arrangement of system installed locations. System locations shall reflect RFP requirements and indicate the type of system.

# TECHNICAL DESCRIPTION

68 POINTS

Attach design documents and narrative that communicate the following information for each site.

    - System description

    - Equipment details and description

    - Conceptual Plan/System Layout

    - Rendering, altered photo, etc. showing a clear visual of the system

    - Description of landscape, fencing, and/or aesthetic features, including landscape removal, lighting, parking islands, etc.

    - List of proposed materials, including batteries, inverters, racking and support systems, structural materials and balance of systems equipment

    - List any plans to address the impact on existing Trustees warranties, and the plan for assumption of any impact resulting to Trustees property from installation, maintenance, or operation of the Systems

    - Performance of equipment, subsystems, and site-specific components

    - Integration of systems with Trustees’ existing electrical systems

    - Electric utility provider interconnection requirements

    - Controls, instrumentation, monitoring, and data management capabilities

    - Proposed locations for the system equipment and related components

    - Proposer shall provide the following technical description of the technologies proposed for installation at the specific sites:

      - Configuration, including tilt angle and aspect

      - Structural requirements

      - Typical  useful  life  of  significant  components

      - Benefits specific to the systems proposed

      - Any product or warranty enhancements being offered

      - Description of the manufacturer of the batteries and relevant information regarding the manufacturer’s environmental plan, such as ISO 14001

      - Other relevant information

Note: The Trustees will review and approve all system design and construction documents, particularly for its visual impact on surrounding buildings and public spaces, visibility to passersby, glare and reflectivity, and the appearance of exposed edge of panels. Inclusion of photographs and architectural elevations are required. Please include the height(s) of the proposed system(s).

# METERING & MONITORING DESCRIPTION WITH DATA ACCESS

48 POINTS

Proposer shall provide a description of the monitoring system that will be installed at the specific sites, including:

- Equipment/instrumentation  –  proposed  system  to monitor and track  system  electrical energy output and diagnose system underperformance

- Monitoring data points – values being monitored and stored by the system

- Analysis and data reduction of monitored values – results presented and stored by the system

- Format and storage of raw and reduced data – protocol and format of stored data

- Access to raw, reduced and stored data – protocol for accessing data

- Maintenance and operation requirements including calibration frequency

- Comprehensiveness of data collection, effectiveness of data presentation, ease of data access, ease of integration

- Demonstration and display features for educational, training and research purposes;

- Proposer should assume that data storage, management and display shall be included within the proposal.

- Systems shall be accessible by the Trustees with real time data that includes 15-minute demand intervals and energy totaled by the time of use periods in local utility company applicable tariff(s) rate noted on the Campus specific MEA coversheet.

Proposer shall provide a plan for metering, monitoring, diagnosing, and tracking the battery energy input/output of the systems consistent with Trustees requirements. A minimum requirement for the data monitoring and access is a web-based monitoring and tracking system accessible to the Proposer, Trustees. This system must include real-time or near real-time data on electricity input/output by the system as an open and accessible source to Trustees.

# PROJECT SCHEDULE

74 POINTS

Proposer shall provide a detailed CPM project schedule (timeline) below, for each proposed installation as well as an overall completion schedule, showing all major events, planned start and finish dates, dependencies between tasks, proposed deliverable dates, and significant milestones. Proposer must also include proposed options for the continuation or removal of the system at the end of the contract term as specified in the ESSLSA.

As indicated on the Campus Specific Storage MEA Coversheet, the Successful Proposer shall be required to address failure to meet all installation deadlines in one of the two following ways: (1) make the site safe and return the site to its original use (e.g., parking spaces, and parking lot driveways are available for public parking); or (2) pay a per liquidated damages for each day a site is unavailable.

# PROJECT TEAM ORGANIZATION

13 POINTS

The Trustees require that a Team Organizational Chart be developed and provided as part of the Proposal. Please identify all of the proposed key personnel, as identified in Section 5.6, below, of each team component and how the team will be managed. Once accepted, any changes to the Project Team or Key Personnel must be approved by the Trustees. The Trustees reserve the right to interview each new team member to confirm its acceptance of the new team member and any new Key Personnel. If the Trustees do not accept a proposed new team member, Proposer will provide alternative team members of equal or better qualifications until such time that the Trustees accepts the proposed new team member. The Trustees expects the Successful Proposers Key Personnel to be committed to the Design and Installation portion of the Project for the duration of their role, and the Successful Proposer will not roll personnel on and off the Project without approval of the Trustees. The Trustees also reserve the right to ask Proposer to remove a person from the Project team at the Trustees discretion In addition to the Team Organizational Chart, Proposer shall include the following team information:

    - Names of other team member firms and the persons from those firms dedicated to this program;

    - Roles and responsibilities of each team member, and the relationship between the team members, include an organizational chart;

    - A brief description of each team member’s firm and their ability to contribute to successful energy storage program implementation (history, performance of similar scope of services, etc.);

    - History of past projects that the team members have worked on together. If a single firm submits the proposal, then the following information shall be provided:

      - Roles and responsibilities of key personnel

      - Organizational chart

    - Identify any subcontractors Proposer intends to employ in execution of the program. Discuss their role and provide information on subcontractors’ experience performing similar work. Provide information as to how Proposer plans to manage subcontractors to ensure that the needs of the Trustees will be met and all subcontractors meet any and all applicable laws and campus procedures.

# QUALIFICATIONS OF KEY PERSONNEL

34 POINTS

Proposer shall include resumes of key personnel who will be assigned to this project. Key personnel are defined as, but not limited to the following: Project Manager, Project Engineer, Project Planner, Structural Engineer, Project Architect, Construction Project Manager, and Construction Field Superintendent.

# PAST-PROJECT EXPERIENCE

30 POINTS

Proposer shall provide a brief description of three (3) completed battery energy storage projects/programs that are similar in nature and size as those expected to result from this RFP.  The description for each project/program should include:

    - Project name

    - Location

    - Project size (total cost and project AC capacity in kW)

    - Project type – turnkey or third-party demand reduction sales

    - Project performance – expected vs. actual output

    - Year completed

    - Name of project manager

    - Name of client and contact information

    - Brief physical description of the project (equipment manufacturer, model, etc.)

    - Photographs, if available

    - Describe experience with California’s Rule 21 electrical interconnection, particularly for non- export generating facilities

    - A brief discussion of any specific challenges and how they were overcome

    - Review of project schedule – award date,  installation  completion  date  and  date  of commercial operation

# REFERENCES

13 POINTS

For each of the projects in Section 5., above, Proposer shall provide below the client reference information - including name of client contact, company name, title, address, phone number, email address. At a minimum, at least three of the projects must have been completed within past five years and been for demand reduction on battery energy storage projects/programs. The references shall be for projects of comparable size to the proposed installation and for projects that were installed, owned, operated and maintained by Proposer.

# MANAGEMENT AND STAFFING PLAN

26 POINTS

Proposer shall be responsible for developing a Management and Staffing plan which illustrates the management approach to performing the Work to meet the project schedule and deadlines.

The Management and Staffing Plan must indicate all staff required to complete the Work through all phases. Proposer shall also provide a table or matrix showing Proposers current and pending major project commitments. Proposer must provide a detailed project schedule with a timeline including dates and milestones.

# OPERATION AND MAINTENANCE PLAN

64 POINTS

Proposers shall submit an Operation, Maintenance, Service, and Monitoring Plan for the project, as described in Items 1 and 2 below. Additionally, a Billing Plan consistent with the Price Proposal is required for the duration of the contract term, as described below. Proposer shall provide Operations and Maintenance (O&M) services for the full project term as set forth in the ESSLSA.

Proposer shall describe the proposed O&M procedures for the System(s) and shall describe its experience providing such services for similar energy storage installations and shall provide information on the personnel performing the O&M service.

# BILLING PLAN

21 POINTS

Proposer shall submit a Billing Plan that includes the following:

    - The billing system to the Trustees shall be consistent with the Cost Proposal Form

    - A method to document the demand reduction and costs of energy system inputs/outputs.

    - An annual/monthly adjustment or true-up process to ensure accounting that is compliant to guarantees.

    - A preferred method for the sharing of billing data and information such as online, email, or third-party access

    - The monthly billing period should coincide with the local utility provider billing cycle and shall include the following:

      - Peak Demand Reduction in kW (AC) during time of use periods and season (winter/summer)

      - Total kWh (AC) input by time of use period

      - Total kWh (AC) output by time of use period

      - Calculated round trip efficiency as percent.

      - Total kWh (AC) costs by inputs delivered to the Trustees by time of use period

      - Total kWh (AC) costs by outputs delivered to the Trustees by time of use period

      - Value or cost of energy arbitrage

      - Price of Peak Demand Reduction in $/kW for the month

      - Amount due for peak demand reduction sold to the Trustees within the billing period

      - Past due amounts

      - Total Bill

# Exceptions to ESSLSA

25 POINTS

Proposer shall list any and all exceptions to the Energy Storage Site License Service Agreement (ESSLSA) on an item-by item basis and cross-referenced with ESSLSA document.* If no exceptions are taken, Proposer must expressly state there are no exceptions taken to receive full points.   2 points will be deducted from the 25 total points available for each minor exception, 4 points for exceptions to major items such as appropriations, indemnification, consequential damages, and insurance.

*NOTE: Proposers are reminded that unacceptable exceptions taken to RFP or ESSLSA provisions may render Proposer’s submittal non-responsive and subject to disqualification.

# CAPITAL FINANCE STRUCTURE

17 POINTS

Proposer shall provide information regarding the capital finance structure of the privately-owned system, which should include:

- Description of relevant financing structure for proposed project

- Identification of funding sources

- Examples of previously funded or financed third-party owned projects

- Commitment letter from anticipated funding source and the credit rating of each funding source

- For financing team members, provide Moody’s, Fitch, or Standard & Poor credit rating and three years annual report or audited financial statements

# SUSTAINABILITY CAPABILITIES

26 POINTS

Proposer shall complete Form 3 Sustainability Capabilities.

# SIMULATED PEAK DEMAND REDUCTION

DATAPASS/FAIL

Proposer shall provide simulated hourly Peak Demand Reduction data (i.e., 8760) for each system in Microsoft Excel format. This information will not be scored separately and should not be provided in printed form.  This data should be provided electronically on USB along with the electronic submission of the main proposal.

# SECTION COST PROPOSAL

All proposals shall be submitted with the understanding that the prices quoted shall remain in effect for the entire term of the Energy Storage Site License Service Agreement (ESSLSA).

# COST PROPOSAL SUBMITTAL

Cost proposals must be submitted on the Cost Proposal Form provided by the Trustees, on or before the date and time listed on the Campus specific storage MEA coversheet. Sealed envelope shall be marked as follows:

Cost Proposal

Systemwide Storage Project

California State University,

[Campus Name From Storage MEA Coversheet]

Proposer's Name and Address

# ACTUAL PEAK DEMAND REDUCTION PRICE

The pricing for the Actual Peak Demand Reduction will be a fixed price rate rounded to the nearest 10th of a cent per Kw (AC) with either no annual escalator. The price shall include any applicable Renewable Energy Credits (REC’s) over the ESSLSA term.

# BASIS FOR AWARD

Award shall be based on the highest point total.

# ESTABLISHMENT OF SUCCESSFUL PROPOSAL

At the Cost Proposal opening the following formula will be used to determine the points awarded to the cost proposal. The Cost Proposal will be scored in direct relation to its variance from the lowest cost based on the average cost. The lowest Cost Proposal will receive the maximum score. Cost per kW will be calculated by the Trustees using the proposed rate, as reflected in the bid sheets.  Proposers that elect shared savings percentage pricing will be scored by Trustees converting shared savings fractions into price per kW for comparison purposes. Note: Trustees favor true shared savings for sharing of risk and will award 30 Bonus points for shared savings proposals.

For example:

| Proposed $/kW | Variation from Lowest $/kW= Proposed $/kW– Lowest $/kW | % Variation = Variation from lowest $/kW / Average $/kW | Points to deduct from 300 points | Fee Score |
| --- | --- | --- | --- | --- |
| $5/KW | 5-5=0 | 0/5.5=0 | 300 x 0=0 | 300-0=300 |
| $5.50/KW | 5.5-5=0.5 | 0.5/5.5=9% | 300 x 9=27 | 300-27= 273 |
| $6/KW | 6-5=1 | 1/5.5=18% | 300 x 18=54 | 300-54=246 |

Sample Calculation:  Average $/kW = (5+5.50+6)/3 = 5.50

# AWARD

Award will be made to the Proposal having the greatest sum of technical and cost proposal total points.  Projects will be awarded by Campus, or by groups of Campuses, as indicated in the Campus Specific Storage MEA Coversheet. THE DECISION OF THE TRUSTEES IS FINAL

# NOTICE OF INTENT TO AWARD

A "Notice of Intent to Award" will be emailed to all Proposers effective for a time period of three (3) working days prior to award.

To:	Campus Contact:  XXX	Date:  XXX	California State University, [Campus Name]

    - In compliance with your Request for Proposal, our bid is as follows:

Cost for Trustees Sites X, X, and X with M&O	$XXX	per kW (AC)

Or Percentage of Peak kW Savings: _____________

    - In compliance with your Request for Proposal, our cash price bid is as follows:

Cash Price option for CSU Sites X, X, and X 	$XXX

    - Proposers shall assume $250,000 in Rule 21 interconnection costs as part of their bid price entered above and complete the schedule below in the event actual costs are less than or greater than $250,000.

| Change in interconnection costs | Change in rate ($/KW) |
| --- | --- |
| -$50,000 |  |
| -$40,000 |  |
| -$30,000 |  |
| -$20,000 |  |
| -$10,000 |  |
| +$10,000 |  |
| +$20,000 |  |
| +$30,000 |  |
| +$40,000 |  |
| +$50,000 |  |

I hereby agree to perform said work in accordance with the terms and conditions set forth in the above-referenced Request for Proposal and executed ESSLSA.

______________________________________________

Signature

Name/Title:  XXX

Name of Company as Licensed:  XXX

Contractor License Number  (If Applicable):  XXX

Address:  XXX

City, State Zip:  XXX

Telephone Number:  XXX

Federal I.D.:  XXX

# SECTION 7 – PREPARATION AND FORMAT

All proposals shall be submitted in the format identified in this section. All requirements and requested information shall be addressed. The Trustees reserve the right to request information deemed missing from a Proposer’s submittal or request clarifying information as necessary to ensure that each Proposal is complete according to the requirements of this RFP.

# NUMBER OF COPIES

Proposer shall provide one (1) original set of the proposal (marked as such) and one electronic copy (CD or USB).

# DELIVERY OF PROPOSALS

Sealed proposals shall be delivered by mail or in person to:

[Campus Contact for Solicitation]

California State University,

[Campus Name]

[Campus Address From Coversheet]

Proposals must be received no later than the date and time specified on the cover page.

LATE PROPOSALS WILL NOT BE ACCEPTED.

Proposals shall be labeled:

#### Systemwide Storage

#### Project – [CSU Campus]

#### Technical Proposal

Delays due to the various methods used to transmit the proposal including delays by the internal mailing system at the University will be the responsibility of the Proposer. Delays due to inaccurate directions given, even if by University staff, shall also be the responsibility of the Proposer. The proposal must be completed and delivered in sufficient time to avoid disqualification for lateness due to any and all difficulties in delivery.

# PROPOSAL FORMAT

Proposals shall adhere to the format identified in this Section. Proposals must be divided into the individual sections listed below, indexed and tabbed.

Request for Proposal Requirements

Cover Letter

Proposer is required to submit a signed cover letter with the proposal response. The signature on the cover letter shall be from a duly-authorized officer representing the Proposer’s firm having legal authority in such transactions. Unsigned proposals shall be rejected.

The cover letter shall include the following:

    - Company name, address, telephone, email address, fax number and Federal ID number

    - Acknowledgement of receipt of any RFP addenda

    - Name, title, address, phone and email address of contact person

Tab 1 	Table of Contents

Proposer shall provide a table of contents in a format consistent with the proposal requirements and format set forth herein.

Tab 2	Exceptions to RFP Terms and Conditions

Proposer shall list any and all exceptions to the RFP on an item-by-item basis and cross-referenced with the RFP document.* If there are no exceptions, Proposer must expressly state that no exceptions are taken.

Tab 3	Exceptions to ESSLSA Terms and Conditions

Proposer shall list any and all exceptions to the Energy Storage Site License Service Agreement (ESSLSA) on an item-by item basis and cross-referenced with ESSLSA document.* If no exceptions are taken, Proposer must expressly state there are no exceptions taken.

*NOTE: Proposers are reminded that unacceptable exceptions taken to RFP or ESSLSA provisions may render Proposer’s submittal non-responsive and subject to disqualification.

Technical Proposal

Tab 4		Small Business, DVBE, and Incentives

Reference Section III, Paragraph 3.4 and Paragraph 3.5

Tab 5		System Size and Output

Reference Section V, Paragraph 5.1

Tab 6		Technical Description

Reference Section V, Paragraph 5.2

Tab 7		Metering and Monitoring Description with Data Access

Reference Section V, Paragraph 5.3

Tab 8		Project Schedule

Reference Section V, Paragraph 5.4

Tab 9		Project Team Organization

Reference Section V, Paragraph 5.5

Tab 10		Qualifications of Key Personnel

Reference Section V, Paragraph 5.6

Tab 11		Past-Project Experience

Reference Section V, Paragraph 5.7

Tab 12		References

Reference Section V, Paragraph 5.8

Tab 13		Management and Staffing Plan

Reference Section V, Paragraph 5.9

Tab 14		Operation and Maintenance Plan

Reference Section V, Paragraph 5.10 (Sections 1 and 2)

Tab 15		Billing Plan

Reference Section V, Paragraph 5.11

Tab 16		Lighting

Reference Section V, Paragraph 5.12

Tab 17		Capital Finance Structure

Reference Section V, Paragraph 5.13

Tab 18		Attachments

Reference Section V, Paragraph 5.14

Tab 19		Simulated Charge/Discharge Data

Reference Section V, Paragraph 5.15