# RIDER E - SCHEDULE

DEVELOPMENT & INSTALLATION AND CONSTRUCTION

| DEVELOPMENT |  |  |  |
| --- | --- | --- | --- |
| Task | Milestone | Responsible Party | Reference |
| Notice of Intent to Award |  | Trustees |  |
| Fully Executed Solar License and Power Purchase Agreement | Due on or before month, day year | Trustees and Licensee |  |
| Licensee pays 1st Transaction Fee | Due after month, day, year before month, day, year | Licensee | Section 3.9 of the Agreement. |
| Notice to Proceed to Design |  | Trustees |  |
| Project Kick-off Meeting | Before or at delivery of Schematic Design | Licensee & University | As mutually agreed to by the Parties |
| Schematic Designs | On or before Month, day, year | Licensee | Section 7.8 of the Agreement includes schematics, equipment data sheets and proposed schedule |
| Review of Schematics | Five (5) Business Days | Trustees | Section 7.8 of the Agreement |
| Resubmittal of Schematics (if required) and approval | 15 days from receipt of Trustees’ changes and/or comments | Trustees | Section 7.11 of the Agreement |
| 95% Construction Documents | On or before month, day, year | Licensee | Section 7.9 Agreement includes detailed plans, specifications, engineering calculations and updated schedule |
| Trustees’ Review of Construction Documents | Fifteen (15) Business Days from receipt of Construction Documents | Trustees | Section 7.9 of the Agreement |
| Technical Review of Construction Documents | Concurrent with Trustees’ review | Trustees and Licensee | State Fire Marshal, Seismic, Mechanical Review Board |
| Re-submittal of Construction Documents (if required), and proposed abatement contractor | 15 days from receipt of Trustees’ changes and/or comments | Licensee | Sections 3.3.1 and 7.11 of the Agreement |
| Final Back Check of Construction Documents and approval of CD’s, and abatement contractor | On or before Month, day, year | Trustees |  |
| Performance Bond and Insurance Certificates | Due prior to beginning any construction | Licensee | Section 8.9 and Article 18 of the Agreement |

| INSTALLATION AND CONSTRUCTION |  |  |  |
| --- | --- | --- | --- |
| Task | Milestone | Responsible Party | Reference |
| NOTICE TO PROCEED | 5 working days from approval of Construction Documents | Trustees | Section 8.2 of the Agreement |
| Licensee pays 2nd Transaction Fee | To be paid on or before month, day, year | Licensee | Section 3.9 of the Agreement. |
| Actual Construction Start Date | Within 10 days, but no sooner than month, day, year | Licensee | Section 8.3 of the Agreement |
| Construction and Installation (including Trustees’ inspection) | Work may occur between Month, day, year and month, day, year. | Licensee and Trustees | Section 8.15 of the Agreement inspection of the work for compliance with approved plans, applicable codes and regulations |
| Construction Installation and Completion | Written notification no less than 10 days and no more than 15 days before COD | Licensee | Section 8.7 of the Agreement |
| As-built Drawings including Project Manual | Prior to COD or in accordance with the Agreement | Licensee | Section 7.13 of the Agreement Section 9.5 of the Agreement |
| Final Inspection and Testing as required by Trustees | After written notification and prior to COD | Trustees | Requires utility sign off and execution of interconnection agreement |
| Notice of COD | Written notice within 24 hours of occurrence | Licensee | Section 8.7 of the Agreement |
| Commercial Operation Date | No later than Month, day, year | Licensee | Section 8.4 of the Agreement |
| Licensee pays 3rd Transaction Fee | To be paid within 15 days of the date the Licensee achieves financial close in its financing. | Licensee | Section 3.9 of the Agreement. |
| Punch List | Within 15 days after Notice of COD | Trustees | Section 8.8 of the Agreement |
| Completion of Punch List | Within 30 days of receipt | Licensee | Section 8.8 of the Agreement |
| Legal Description | Within 60 days of COD | Trustees | Section 3.13.3 of the Agreement |

End of Rider E

Milestones for which Licensee is the responsible party, including the Guaranteed Construction Completion Date, will be extended on a day-for-day basis for any delays in Trustee’s performance of its obligations under this Agreement.